## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 09/05-09/26 | 1.Assigned the group roles, set up the goal of establishing an AI resume analysis application, finished initial requirement analysis 2. Set up the Github work flow, including rulesets, issue templates and PR templates 3. Set up the FrontEnd repo and implement the inputing and uploading files features | N/A | 1. New member joined, causing the reassignment of group roles. 2. Not familiar with the Github settings | 1. Rescheduled group meeting time to improve efficiency, set up initial goals for clearer responsibility assignment 2. The improvement will be gradually added in the process of developing | 0 | 8 | 4 | 4 | 0 | 38 | 30 | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 09/27-10/17 | Finished: 1. User story: Resume Analysis 2. Initial integration of CI/CD 3. Manually added some unit tests. 4. Setup of QDrant(vector database) and MongoDB(general database). 5. Publishment of Docker image. 6. Docker deployment on Google Cloud. In progress: 1. User story: Resume Evaluation with job description(dataset, implementation) | N/A | Lack of JD Data | 1. Integrated Git commit plugins to conform Conventional Commit and generate CHANGELOG 2. Integrated CI/CD to auto test, deploy. | 1 | 2 | 11 | 10 | 1 | 234.9 | 197.4 | 43 | 47 | 15 | 5 | 60 | 6 | 26.9 | 41.5 | 21
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Linchen Xu | Finish relavant SPPP documents(Overview, Related Work(Jobscan, Simplify), Essential Features, References, Glossary) | 1. User stories (with relavant tasks): 1.1 Login via Google 1.2 Resume analysis 2. Managed corresponding tasks and issues | 1. Provide API documentation | N/A | Prepare for Iteration 0 Presentation | Frontend: 1. Finish Q&A page interactions 2. Finish resume upload, resume analysis, login, ask questions APIs. Backend: 1. Add CORS to ensure connectivity between frontend and backend. | Added login test for frontend | Set up git | 1. Lead the weekly meeting 2. Participate in other communications
Lin Ma | Fill out the part of Configuration Management Plan |  | Lead all members to fill the designs and implementations in the SDD. |  | Iteration1: Present the work flow from a user story to the release |  | 1. Set up the UF for FE | 1. Set up git rulesets, git commit rules, issues and PR templates 2. Set up CI/CD with Github Actions | 1. Sycn the work flow with team members
Zhen Cao
Zihan Zhou
Haochen Sun

## Linchen Xu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader, Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 10 | 7 | 3 | 0-learn ATS and RAG, read several relavant documents; 1-analyze potential projects; 5- lead the weekly meeting; 7-research for documents related to AI resume analysis | 3 | 1 | 0 | 0 | 0 | 3 | 0 | 3 | 1. Propose AI resume analysis as group project 2. Research for relavant projects | 1. Not farmiliar with other members, still working on communication | 1. Increase the frequency for communication | 1. Analyze AI resume Analysis project based on items in SPPP, finish relevant items in the document and discuss them in the next weekly meeting. 2. Dicided that Zhen Cao will do relevant researches on datasets of resumes 3. Set up git 4. Finish Lab1 | 15
2 | 09/12-09/18 | 19 | 16 | 3 | 1- Finish relavant SPPP documents(Overview, Related Work(Jobscan, Simplify), Essential Features, References, Glossary) 6- Set up git 7- FInish Lab1 | 0 | 14 | 0 | 0 | 0 | 3 | 1 | 1 | 1. Finish relavant SPPP documents(Overview, Related Work(Jobscan, Simplify), Essential Features, References, Glossary) | 1. Unknown member(Haochen Sun) trying to join our group, failed in communicating with this member | 1. Sent an email to the new member(Haochen Sun) asking for a brief discussion after next week's course | 1. Prepare for iteration 0 presentation | 10
3 | 09/19-09/25 | 12 | 10 | 2 | 1- Finish and update relavant SPPP documents(Management Plan) 7- Prepare for Iteration 0 presentation | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 5 | 1. Finish relavant SPPP documents(Management Plan) 2. Prepare for Iteration 0 presentation | 1. Assigned the Requirement Leader role to Haochen Sun, but I have to prepare for presentation due to limited time. | 1. Prepare for presentaion based on existing items in SPPP. | 1. Break down invidual tasks by week, review them by 09/28. 2. Start developing the project 3. Finish Lab2 | 15
4 | 09/26-10/02 | 14 | 10 | 4 | 0-Read Module 2's slide 1-Finish lab2 3-Finish basic functionality of Q&A page and part of API functions 5-Participate in Sunday's meeting, and take charge in Thurday's weekly meeting. Participate in Discord's communicaitons. | 3 | 1 | 0 | 6 | 0 | 4 | 0 | 0 | 1. Finished basic funcionalities of Q&A page | 1. Unable make full contribution due to illness. 2. The required API schema is not provided yet. | 1. Already recovered. 2. Planning to take charge of defining the schema. | 1. Finish API schema definition. 2. Complete Q&A and API implementation that are not completed. 3. Prettify Q&A page. | 15
5 | 10/03-10/09 | 17 | 15 | 2 | 0-Read Module 1's and Module 2's slide, FInish Quiz 1. 1-Analyzed user storied and updated Lab2 3-Prettified Q&A page, implemented upload and login API. 5-take charge of weekly meeting | 5 | 2 | 0 | 8 | 0 | 2 | 0 | 0 | 1. Prettified Q&A page. 2. Implemented upload and login API. | 1. Had trouble integrating Google login API. | 1. Resolve the issue with Adam Ma | 1. Prepare for iteration 1's presentation. 2. Implement Login via Google OAuth2. 3. Test connectivity between frontend and backend. | 15
6 | 10/10-10/16 | 15 | 11 | 4 | 0-Learn windtail CSS 3-Prettify Q&A page and make sure frontend and backend communicates properly 4-Write tests 5-Hold weekly meeting, participate in communications 7-Write documents | 1 | 0 | 0 | 7 | 1 | 4 | 0 | 2 | 1. Implemented resume analysis 2. Prettified Q7A page, added unit test 3. Ensured connectivity between frontend and backend | 1. Did not finish login API | 1. Finish login API next week | 1. Finish login API and ask questions API. 2. | 10
7 | 10/17-10/23 | 0 | 0
8 | 10/24-10/30 | 0 | 0
9 | 10/31-11/06 | 0 | 0
10 | 11/07-11/13 | 0 | 0
11 | 11/14-11/20 | 0 | 0
12 | 11/21-11/27 | 0 | 0
13 | 11/28-12/04 | 0 | 0

## Lin Ma
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader, Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 13 | 10 | 3 | 0-Learn the Aglie and software management docs 1-Analysis of my proposals 5- Communicate with team members about my proposals | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Propose three projects, including an Education game like Duolingo, a new cryptocurrency and a quantitative program. 2. Provide the FE design of the final project. | 1. Not familiar with other members, still working on communication 2. Not familiar with RAG. | Learn and search resource on Internet | 1- Finish relavant SPPP documents(Configuration Management Plan) 1- Finish a part of SDD documents (FE design and diagrams) 5- Notify other team members to fill in the SDD doc. | 5
2 | 09/12-09/18 | 13 | 10 | 3 | 1- Finish relavant SPPP documents(Configuration Management Plan) 1- Finish a part of SDD documents (FE design and diagrams) 5- Notify other team members to fill in the SDD doc. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fill relevant docs |  |  | 0- Learn how to create templates of Github issues and PR 0- Learn how to create Git rulesets on Github 3- Implementation of inputing and uploading files 5- Notify the PRs, results on Discord 6- Implementation of templates of Github issues and templates and the rulesets | 15
3 | 09/19-09/25 | 29 | 27 | 2 | 0- Learn how to create templates of Github issues and PR 0- Learn how to create Git rulesets on Github 0- Learn how to integrate the tailwinds into Vite and React 0- Learn what kind of CI/CD flows and tools is better 0- Learn the rules of Git commit and versioning (Conventional commit, semantic versioning) 1- Analysis of the User story about inputing and uploading files. 2- Design the UI/UX 3- Implementation of inputing and uploading files 5- Notify the PRs, results on Discord 5- Helping members to solve the Git issue 6- Implementation of templates of Github issues and templates and the rulesets 6- Set up the FE repo and integrate it with tailwinds, pnpm, Vite | 6 | 0.5 | 0.5 | 6 | 0 | 2 | 12 | 0 | 1. Enhance the dev experience of Github work flow 2. Establish the conventions about the releases and main branch 3. Investigate the CI/CD flows and tools. 4. Set up the FE repo and deliver two features. | 1. Members are not familiar with these tools and rules 2. There are too many CI/CD tools to ensure which one is suitable for us 3. Configuration items will consume a bunch of time | 1. Break down the tasks and assign them to the members who is interested on it 2. Integrate the CI/CD ability (docker, PR pipelines) 3. Integrate the Git Commit tools 4. Prepare a webniar to showcase the whole work flow 5. Prepare the next presentation | 1. Break down the tasks and assign them to the members who is interested on it 2. Integrate the CI/CD ability 3. Integrate the Git Commit tools 4. Prepare a webniar to showcase the whole work flow 5. Prepare the next presentation 6. Finish the Lab2 | 30
4 | 09/26-10/02 | 23.2 | 22.2 | 1 | 2- Break down the tasks and assign them to the appropraite person 2- Write the postmortem template and summary 2- Lab2 assignments 5-Weekly scrum 6- Integrate cz (a git commit plugin) to implement the Conventional Commit rules (1h + 0.5+0.1+6) 6- Integrate Docker to our repo and update the README about how to use it (1h + 0.5+0.1+6) 6- Integrate Github Action as a CI tool (2) 6- Integrate vitest as a UT tool for the FE(3) | 4 | 0 | 1 | 0 | 0 | 1.2 | 16 | 0 | All of items | Members are not familiar with tools like pnpm, docker | 1. Book a webinar to showcase it (git commit tools and docker) | 1. Prepare a webniar to showcase the whole work flow 2. Prepare the next presentation 3. Integrate CD ability | 30
5 | 10/03-10/09 | 22.2 | 21.2 | 1 | 0-learn Google lab: Implement DevOps Workflows in Google Cloud, and earn a badge 0-learn Google lab: Kubernetes in Google Cloud, and earn a badge 0-learn Google lab: Google Cloud Essentials, and earn a badge 0-learn Google lab: Baseline: Infrastructure, and earn a badge 5-Weekly scrum 6-Publish Docker image to adamma1024/cvcoach_web:v1.0 to the Docker hub 6-Deploy the cvcoach image on GCP EC2 instance | 12 | 0 | 0 | 0 | 0 | 1.2 | 8 | 0 | 1. Publish and deploy the docker image on EC2 | Spend too much time | NA | 1. Prepare the next presentation 2. Integrate CD ability | 40
6 | 10/10-10/16 | 43.5 | 42.5 | 1 | 0-Learn the knowledge of Github Actions(How to trigger the release/published), Nginx(How to proxy ip and domain/subdomain), Docker(How to push, pull, login), Domain(How to set the DNS). 2-Design the outline of the presentation. 3-Record the video and edit the video with music, subtitle. 3-Make the Slides of presentation. 4-Test the whole process of CD pipeline and deployment on the EC2 4-Test the Domain 5-Weekly scrum 5-Talk with ZhenCao and LinChen Xu about the backend's implementation and PR reivew. 6-Add CD pipeline to auto publish docker image 6-Add CD pipeline to auto deploy the latest docker image as releasing 6-Purchase an domain "cvcoach.site" and config the Nginx and DNS to map our service to the domain 6-Add CHANGELOG.md 7-record a development workflow for the presentation | 2 | 0 | 2 | 10 | 1 | 1.5 | 16 | 10 | 1. CD pipeline for auto publishing the docker image 2. CD pipeline for auto deploying the latest image on EC2 3. Purchase a Domain and config Nginx to map to it. 4. Host the Domain on Cloudflare for security supports. 5. Work on Presentation stuff | Spend too much time | NA | Do some backend jobs | 2
7 | 10/17-10/23 | 0 | 0
8 | 10/24-10/30 | 0 | 0
9 | 10/31-11/05 | 0 | 0
10 | 11/06-11/12 | 0 | 0

## Zihan Zhou
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Sequrity Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/11 | 9 | 6 | 3 | 0 - learn git 1 - define ensential requirements 1 - research interation sequrity requirements 0 - learn sequrity analyze 5 - make project plan 7 - research similar products | 3 | 2 |  |  |  | 0.5 |  | 0.5 | 1. Write SPPP 2. Set up git, commit a self intro message on git | 1. not familar with git | 1. Ask Lin Ma for help | 1. finish security analyze | 5
2 | 09/12-09/18 | 9 | 5 | 3 | 1 - define high level requirements, 6 - set up git 0 - learn RAG 1 - Finish security analyze | 1 | 2 |  |  |  |  | 2 |  | 1. Finish SPPP documents | 1. not familar with security control software | 1. self learning | 1. Decide interation 1 requirements | 4
3 | 09/19-09/25 | 8 | 4 | 2 | 2 - design RAG work flow 1 - analyze 1st interation needs 5 - communicate about backend job |  | 2 | 1 |  |  | 1 |  |  | 1. Draw simple back end work flow | 1. Not sure the actual needs for interation 1 | 1. Discord with team memebers | 1. Start implement | 3
4 | 09/26-10/02 | 8 | 7 | 2 | 0 - learning how to set up vector database 2 - design the work flow of database to API 0 - learn how to use google authtication 3 - implement google authtication 5 - discuss about Rsume analyze and grading | 1 |  | 1 | 3 |  | 2 |  |  | 1. Coding for google authtication | 1. Not very clear about the specific resume grading levels | 1. Planned discusstion with teammates on discord | 1. Run the vector database upload pipeline automatically | 6~7
5 | 10/03-10/09 | 9 | 9 | 3 | 3 - implement google authtication 3 - implement local qdrant database set up 3 - iplement cloud qdrant database set up and coding 0 - learn about bash and how to connect to the qdrant cloud 5 - peer review code and discuss about 2 level of the resume grading | 2 |  |  | 6 |  | 1 |  |  | 1. Delivered the data embedding and upload 2. Mostly done with google authtication | 1. Google authtication has problems with service set up | 1. Planned to discuss inperson to look for a solution | 1. Start design and implement the RAG retrieve plan | 8~9
6 | 10/10-10/16 | 9 | 7.5 | 3 | 2 - design RAG retrival pipeline 3 - Fix google authtication port issue 5 - Communicate about interation one PPT 5 - Mock presentation for interation one 3 - Record Demo video for the demo program 4 - Test Google authtication 6 - Config local environment for frontend |  |  | 1 | 2 | 1 | 3 | 0.5 |  | 1. Design retival pipeline 2. Record demo video 3. Google authtication 4. One slide contribution to the PPT | 1. The login page and authtication haven't had any solid function relation to the project yet | 1. Discussing about database and user authtication | 1. Design and implement the full data retrival | 8~9

## Zhen Cao
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 3 | 3 | 1 | 0 - read several tutorials about RAG | 3 | [8 empty] | 1. not familar with QA | 1. learn about QA | 0 - learn about QA 1 - QA part of SPPP document 3 - find resume dataset | 10
2 | 09/13-09/20 | 7 | 6 | 1 | 0 - learn about QA 3 - find resume dataset 4 - establish coding standards and test tools | 2 |  |  | 1 | 3 |  |  |  | 1. Complete the SPPP document related to QA | 1. not familiar with those test tools | 1. may take 2 weeks to learn and set up those tools | 0 - learn about test tools 2 - backend design and start to implement some functions | 10
3 | 09/21-09/26 | 13 | 10 | 1 | 0 - learn git and flask 2 - create backend flowchart and update relevant document 3 - resume parser 5 - discusse about the AI workflow and backend design | 5 |  | 4 | 1 |  |  |  |  | 1. Implement the resume parser | 1. still not familiar with git PR 2. resume dataset does not include evaluation for each resume | 1. learn about git 2. ask gpt to evaluate each resume based on several key criteria | 0 - learn about git, test on github 2 - implement resume analysis 4 - implement test on github | 25
4 | 09/27-10/03 | 19 | 17 | 2 | 0 - learn flask API and OpenAI API 0 - learn docker 3 - resume upload 3 - preprocessing - resume evaluation by ChatGPT 3 - resume analysis (in progress) 6 - docker set up 7 - lab2 | 3 |  |  | 10 |  |  | 1 | 3 | 1. Implement the resume upload 2. preprocessing - resume evaluation by ChatGPT | 1. have no idea how to integrate RAG with GPT | 1. fiind some OpenAI documents and need to look into them | 0 - learn how RAG works with GPT 2 - combine all resumes dataset found 2 - implement resume analysis 2 - unit test for previous code 4 - implement test on github | 25
5 | 10/04 - 10/10 | 12 | 10 | 2 | 0 - github CI 3 - resume analysis 3 - job description keywords extract | 2 |  |  | 8 |  |  |  |  | 1. Implement resume analysis 2. Job description keywords extract | 1. need to learn about github CI |  | 0 - learn github CI 6 - github CI 7 - presentation 7 - SDD document | 15
6 | 10/11 - 10/17 | 11 | 8 | 3 | 4 - add unit test 4 - gtihub CI 7 - SDD ducument 7 - prepare for presentation |  |  |  |  | 3 |  |  | 5 | 1. Complete the SDD document 2. Unit test 3. Integrate pytest on gtihub CI |  |  | 3 - new features | 20

## Haochen Sun
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/5-09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 9/12-9/18 | 6 | 3 | 3 | 0 - learning git and se principles 5 - communicate with other members about project plan | 1 |  |  |  |  | 3 |  |  | 1. Joined the team and learning about team's project plan. | 1. not familiar with SE project design processes. | 1. Plan to become familiar with group members and follow the same coding style | 0 - continue to learn process of SE. | 6
3 | 9/19-9/25 | 10 | 5 | 5 | 0 - learning about User stories and data models we are going to use 1 - finished the requirement documents for essential features of our project 5 - talk to our team members about future task breakdown. | 3 | 3 |  |  |  | 4 |  |  | 1. finished the requirement documents for essential features of our project 2. review with our team members the requirement documents | 1. not familliar with front-end and back-end communication concepts. 2. need more time to learn about Docker and more advanced skill of Git. | 1. Have been learning about the mentioned unfamiliar things and will try to test using them on my own. 2. Plan to engage more in our project development. | 0 - learning the above mentioned skills and knowledge 5 - learn from my team members about coding and structure of our project. | 10
4 | 9/27-10/3 | 12 | 6 | 6 | 0 - learning about Docker and Jira 1- viewing and analysing the requirement analysis 5- communicate with members about code and docs 7- setting about the criteria about Resume scores | 3 | 4 |  |  |  | 4 |  | 1 | 1. finished setting up the scoring criteria of resumes 2. working on the Jira tasks distribution and user storeis breakdown. 3. get familar with Github actions | 1.when pushing on Github, there is always issues and conflicts, need to learn to resolve them. | 1. learning from Linchen and Lin about more advanced commands and usage of github actions and configurations. | 1.Finish the Jira set up and that everything on it should be well arranged. 2. working on the coding part about the machine learning algorithms. 3. Web scrapping resumes and download to txt files. | 15
5 | 10/4 - 10/10 | 8 | 4 | 4 | 0 - learning about webscrapping 1 - improve the criteria 1- scrape resumes using python 5 - communicate with members about SDD | 3 | 4 |  |  |  | 1 |  |  | 1. help finish SDD 2. looking for dataset 3. webscrapping resumes | 1.none | 1.none | continue looking for more resumes to train our data model | 13
6 | 10/11 - 10/18 | 12 | 7 | 5 | 0 - learning about machine learning algorithms 1 - improve the criteria of the resume analysis 1- scrape resumes using python on Kaggle 5 - communicate with members about SDD | 6 | 4 |  |  |  | 2 |  |  | 1. Jira task setup 2. tracking the datasets and scape more resumes 3. help complete SDD | 1. need more dataset in the right form | 1. not yet solved | scrape more data for our project use. | 12