## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members |  | 1 | 1 | 1 | 25 | team leader and all members | 2024-09-19 | Reassign the group roles if needed | Reassign the group roles | Closed
| Lack of motivation or responsibility |  | 1 | 1 | 1 | 25 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
Communication | duplicate work |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
| worked on wrong components |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
| useless work |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
| inconsistent work |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
Requirements | unclear requirements |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-26 | Discuss the requirements together during next weekly meeting | Discuss the requirements together during next weekly meeting | Open
| scope creep |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-26 | Discuss the requirements together during next weekly meeting | Discuss the requirements together during next weekly meeting | Open
| constant requirements changes |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-26 | Discuss the requirements together during next weekly meeting | Discuss the requirements together during next weekly meeting | Open
Management | improper task assignments |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
| improper planning |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
| lack of management skills |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-09-19 | Specify the responsibilities | Specify the responsibilities | Closed
Technology competence | Not familiar with the framework used |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-19 | Teach unfarmiliar group members after the weekly meeting | Teach unfarmiliar group members after the weekly meeting | Closed
| Not familiar with the programming language used |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-19 | Teach unfarmiliar group members after the weekly meeting | Teach unfarmiliar group members after the weekly meeting | Closed
| Not familiar with unit testing |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-19 | Teach unfarmiliar group members after the weekly meeting | Teach unfarmiliar group members after the weekly meeting | Closed
| Other technology incompetence |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-19 | Teach unfarmiliar group members after the weekly meeting | Teach unfarmiliar group members after the weekly meeting | Closed
| Not familiar with Git |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-09-19 | Teach unfarmiliar group members after the weekly meeting | Teach unfarmiliar group members after the weekly meeting | Closed
Design and implementation | Improper design |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-10-03 | Review the design in the next two weeks | Review the design in the next two weeks | Open
| improper technology stack |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-10-03 | Review the design in the next two weeks | Review the design in the next two weeks | Open
| Messy code |  | 2 | 2 | 2 | 32 | team leader and all members | 2024-10-03 | Review the design in the next two weeks | Review the design in the next two weeks | Open
Testing | Not enough testing |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-10-17 | Add unit tests accordingly | Add unit tests accordingly | Open
Integration and deployment | Not enough time for integration and deployment |  | 3 | 3 | 3 | 27 | team leader and all members | 2024-10-17 | Review the risk in midterm meeting | Review the risk in midterm meeting | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.